Tidsplan for Moderniserings Projekterne (the Modernization Projects)

- TSS HCV Ørstedværket:

  - start Civil Work Nov 2020 (including HV cable trenches)

  - start installation electrical equipment April 2021

  - Hand-Over: Dec 2021

- TSS Roskilde

  - start Civil Work Nov 2020 (including 1st HV cable trenches)

  - start installation electrical equipment April 2021

  - Partial Hand-Over: Dec 2021

  - Dec 2021: preparation 2nd HV trench

  - Final Hand-Over: August 2022

- TSS Marslev

  - start Civil Work July 2021 (including 1st HV cable trenches)

  - start installation electrical equipment Dec 2021

  - Partial Hand-Over: August 2022

  - August 2022: preparation 2nd HV trench

  - Final Hand-Over: April 2023

- TSS Fredericia

  - start Civil Work Jan 2022 (including 1st HV cable trenches)

  - start installation electrical equipment June 2022

  - Partial Hand-Over: Feb 2023

  - Feb 2023: preparation 2nd HV trench

  - Final Hand-Over: October 2023

- TSS Slagelse

  - start Civil Work April 2022 (including HV cable trenches)

  - start installation electrical equipment Sept 2022

  - Partial Hand-Over: May 2023

  - May 2023: preparation 2nd HV trench

  - Final Hand-Over: January 2024